## Dashboard
SIX SIGMA / SSBB PROJECT TRACKING — DASHBOARD
Live summary of all improvement projects ¦ Source sheet: 'Project Tracking' ¦ Data rows 6-85
TOTAL PROJECTS |  | ACHIEVED |  | ON TRACK | NEEDS ATTENTION |  | NO DATA | ACHIEVEMENT RATE
78 |  | 16 |  | 9 | 31 |  | 22 | 20.51%
STATUS BREAKDOWN |  |  | PROJECTS BY BATCH |  | PROJECTS BY LOCATION / UNIT
Status | Count |  | Batch | Count | Location | Count
Achieved | 16 |  | Batch I | 33 | Unit-I | 3
On Track | 9 |  | Batch II | 46 | Unit-III | 42
Needs Attention | 31 |  |  |  | Unit-IV | 26
No Data | 22 |  |  |  | HO | 5
[5 empty] | JSBIL | 1
TOP DEPARTMENTS BY PROJECT COUNT |  |  |  |  | Mackeil | 2
Department | Count |  | PERFORMANCE METRICS
Business Excellence | 4 |  | Avg. Progress % (all projects) | 38%
MBF Operation | 5 |  | Median Progress % (all projects) | 31.99%
Human Resource | 5 |  | Projects w/ Increasing target | 38
Ferro Operations | 4 |  | Projects w/ Decreasing target | 38
Operation | 4 |  | Projects reporting data (non-blank) | 56
DIP Mechanical | 4 |  | Distinct Locations / Units | 6
DRI | 4 |  | Distinct Departments | 42
CPP Operations | 3
DIP Marketing | 3
Central Electrical | 2
DIP Operation | 1
RMHS Electrical | 2
VISUAL ANALYSIS
Note: All figures are formulas linked live to the 'Project Tracking' sheet (rows 6-85) and refresh automatically when that data changes. 'Achievement Rate' = Achieved projects ÷ Total projects.

## Project Tracking
SIX SIGMA / SSBB PROJECT TRACKING SHEET
Participants ¦ Project Theme ¦ Baseline Period, UOM & Data ¦ Target ¦ Monthly Tracking (Jan–Sep) ¦ Location & Department
PROJECT & PARTICIPANT INFO | [6 empty] | PROJECT TYPE |  |  | BASELINE & TARGET |  | MONTH-WISE ACTUAL TRACKING (JAN – JUN) | [8 empty] | PERFORMANCE SUMMARY
S.No | Batch | Employee Code | Participant's Name | Location / Unit |  | Project Theme / Title | Improvement Direction | Baseline UOM | Baseline Period | Baseline Data | Target | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | 2026-07-01 | 2026-08-01 | 2026-09-01 | Average (Actual) | Progress % | Status | Project File | Review date | Comment | Target Date
57 | II | 2762 | Abdur Rowf | Unit-III | Store | Reducing Non moving items of Central store values from 6.3Cr. to <3.15Cr. INR | Decreasing | Cr |  | 6.3 | 3.15 | [11 empty] | No Data | SSBB Project-Abdur Rowf | 2026-08-10 | 1. issue hopper 2.Monsoon wise data for six month 3.inser comment | U6/K6*100
1 | I | 16923 | Akram Imran | Unit-I | Operations | Improve the Avg Productivity of Kiln per Month from 41.18 ton to 45 ton for Kiln#1 | Increasing | TPD | Dec'24 -Sept'25 | 41.18 | 45 | 28.76 | 42.01 | 30.72 | 42.75 | 39.4231 | 42.6667 | 41.7019 |  |  | 38.2902 | -75.65% | Needs Attention | SSBB Project-Akram Imran | 2026-08-10 | 1.Issue hopper 2. Insert comment | 0
13 | II | 5503 | Alok Mandal | Unit-III | Operation | Reduce the average Gox Venting Loss per month from 339 to 180 MT. | Decreasing | [15 empty] | No Data | SSBB Project-Alok Mandal | 2026-08-10 | 1.Issue hopper 2. Insert comment | 0
50 | II | 2954 | Amit Dahari | Unit-III | MBF Electrical | Reduce the Avg Specific energy consumption of MBF per month from 134.4 kWH/THM to 125 KWH/THM. | Decreasing | KWH/THM |  | 134.4 | 125 | [11 empty] | No Data | SSBB Project-Amit Dahari | 2026-08-10 | 1.Issue hopper 2. Insert comment | U6/K6*100
69 | I | 10223 | Amitava Dasgupta | HO | DIP Marketing | Re-establish the tender data base (tender missing) ------- reducing tender processing time from ----- to ----- without adverse implication. |  | Nos | [14 empty] | No Data | SSBB Project-Amitava Dasgupta | 2026-08-10 | 1.Issue hopper 2. Insert comment | 0
73 | I | 10642 | Amitava Mukherjee | HO | Human Resource | Improve the Manpower engagement of HO from -- % per month to --- % per month. | Increasing | 0 | [14 empty] | No Data | SSBB Project-Amitava Mukherjee | 2026-08-10 | 1.Issue hopper 2. Insert comment
59 | I | 47015 | Aniruddha Ray | Unit-IV | Accounts and Finance | Reduce the Invoice processing time of unit IV from --- to -----. | Decreasing | 0 | [14 empty] | No Data | SSBB Project-Aniruddha Ray | 2026-08-10 | 1.Issue hopper 2. Insert comment 3. Aug-26 ( Plan)
52 | I | 4781 | Anupam Basak | Unit-III | Quality | To reduce the Avg Variation of Basicity of Sinter Plant 1 from 0.107 to 0.06 . | Decreasing | 0 | Aug'25-Dec'25 | 0.107 | 0.06 | 0.099 | 0.106 | 0.105 | 0.106 | 0.102 | 0.097 |  |  |  | 0.1025 | 9.574% | Needs Attention | SSBB Project-Anupam Basak | 2026-08-12 | 1.Target to be check 2. insert comment 3. Legacy coal to constrained to used and showing the trends 4. Last two years of Raining season data to be compare | 2026-08-26
36 | II | 0 | Arijit Mondal | Unit-IV | CPP Operations | Increase the Steam Generation rate of 85 TPH Boiler per month from 31048 to 548972 ton/Month | Increasing | Ton/Month | Jan-25-Nov-25 | 31048 | 48972 | 26349 | 38713 | 51859 | 37485 | 40115 | 36362 | 41116 |  |  | 38857 | 43.57% | Needs Attention | SSBB Project-Arijit Mondal | 2026-08-12 | 1. Required work will be completed in Up-coming capital shutdown. | 2026-10-10
37 | I | 45143 | Arun Thatoi | Unit-IV | Central Electrical | Increase Average Load Factor of Unit-IV from 72.49 % to >80 % per Day | Increasing | % | Aug'25-Dec'25 | 72.49 | 80 | 71.28 | 74.85 | 74.86 | 78.85 | 73.82 | 70.31 | 69.4 |  |  | 73.3386 | 11.3% | Needs Attention | SSBB Project-Arun Thatoi | 2026-08-12 | 1.Inser comment
60 | I | 4924 | Ashok kumar Singh | Unit-III | Industrial Relationship | Increase the Contractual Manpower engagement of Unit-III from ---- per month to 100 % . | Increasing | % | [14 empty] | No Data | SSBB Project-Ashok kumar Singh | 2026-08-12 | 1.Inser comment 2. Issue hopper
64 | II | 49844 | Ashutosh Pathak | Unit-IV | BE -DRI Operation | Increased Avg Steam generation per day from 162.8 ton to 180 ton K#1 | Increasing | Ton/Day | Sept'25-Dec'25 | 162.8 | 180 | 165.92 | 178.42 | 165.53 | 153.32 | 158.26 | 142.87 | 161.28 |  |  | 160.8 | -11.63% | Needs Attention | SSBB Project-Ashutosh Pathak | 2026-08-12 | 1.Inser comment 2. Issue hopper
65 | II | 49844 | Ashutosh Pathak | Unit-IV | BE -DRI Operation | Increased Avg Steam generation per day from 162.8 ton to 180 ton K#2 | Increasing | Ton/Day | Sept'25-Dec'25 | 162.02 | 180 | 161.66 | 168.45 | 162.94 | 168.89 | 157.53 | 152.18 | 162 |  |  | 161.95 | -0.3893% | Needs Attention | SSBB Project-Ashutosh Pathak | 2026-08-12 | Review
66 | II | 49844 | Ashutosh Pathak | Unit-IV | BE -DRI Operation | Increased Avg Steam generation per day from 172.28 ton to 180 ton K#3 | Increasing | Ton/Day | Sept'25-Dec'25 | 172.28 | 180 | 172.97 | 165.03 | 162.4 | 191.3 | 189.69 | 179.48 | 155.04 |  |  | 173.7014 | 18.41% | Needs Attention | SSBB Project-Ashutosh Pathak
67 | II | 49844 | Ashutosh Pathak | Unit-IV | BE -DRI Operation | Increased Avg Steam generation per day from 180.68 ton to 185 ton K#4 | Increasing | Ton/Day | Sept'25-Dec'25 | 180.69 | 185 | 162.62 | 167.1 | 173.41 | 168.54 | 169.08 | 172.86 | 165.6 |  |  | 168.4586 | -283.8% | Needs Attention | SSBB Project-Ashutosh Pathak | 2026-08-12 | 1.Inser comment 2. Issue hopper
53 | I | 80428 | Atish Gupta | Mackeil | Sales & Marketing | Improve on time Delivery of Finished Goods in Mackeil per month from 43 to 56%. | Increasing | % | Apr'25-Sep'25 | 43 | 56 | 41.7229 | 49.8789 | 36.9037 | [6 empty] | 42.8352 | -1.268% | Needs Attention | SSBB Project-Atish Gupta | 2026-08-12 | 1.Inser comment 2. Issue hopper
40 | II | 2483 | B.K Mishra | Unit-III | Coke Oven Operation | Reduce the Ash % in Coke of Coke oven plant per month from 12.92 to <12.0 . | Decreasing | % | Jul'25-Dec'25 | 12.92 | 12 | 12.1 | 12.42 | 12.74 | 12.44 | 12.56 | 12.01 |  |  |  | 12.3783 | 58.88% | On Track | SSBB Project-B.K Mishra | 2026-08-10 | 1.Issue hopper 2. Insert comment 3. Aug-26 ( Plan)
55 | I | 334 | Bidyut Bikash Dinda | Unit-III | Coke Oven Mechanical | Reduce the average monthly general Maintenance Cost per ton of Coke Oven Plant from ₹28.6 to <₹25. | Decreasing | ₹/Ton | Jul'25-Dec'25 | 28.6 | 25 | 24.01 | 21.03 | 24.29 | 25.06 | 23.67 | 25.2629 | 20.1978 | 20.01 |  | 23.3601 | 145.6% | Achieved | SSBB Project-Bidyut Bikash Dinda | 2026-08-10 | 1.Issue hopper 2. Insert comment 3. Aug-26 ( Plan)
7 | I | 464 | Binoy Kumar Vishwakarma | Unit-III | Sinter Operation | Reduce the specific energy consumption per ton of sinter from 299887 to <284652 Kcal/TS. | Decreasing | % | Jan'25-Dec'25 | 299887 | 284652 | 308018.8 | 384278.8 | 345679.5 | 309111.7 | 266104 | 255905.3 | 299720 | 283809.343 |  | 309831.1571 | -65.27% | Needs Attention | SSBB Project-Binoy Kumar Vishwakarma | 2026-08-10 | 1.Issue hopper 2. Insert comment 3. Aug-26 ( Plan)
43 | II | 6095 | Biswanath Banerjee | Unit-III | Drawings and Design | Reduce the Invisible Zn losses of DIP per day from 41.03 gram/m2 to 12.0gram/m2 . | Decreasing | Gram/m2 | Jul'25-Oct'25 | 41.13 | 12 | 11.35 | 11.59 | 9.8 | 13.36 | 14.36 | 10.49 | 9.39 | 11.79 |  | 11.4771 | 101.8% | Achieved | SSBB Project-Biswanath Banerjee | 2026-08-12 | 1.Insert comment 2. Issue hopper 3. Review Productivity exclude plan shutdown 4. Power failure Action Plan 5. Monsoon Production losses(compare last year data & change the target | 2026-08-26
47 | I | 48356 | Gourav Sarkar | Unit-IV | BE -RM Operation | Reduce Average Specific Power Consumption of Induction Heater Per Day from 41 to 25. | Decreasing | Kwh/MT | Sep'25-Dec'25 | 34 | 25 | 22 | 22 | 22 | 20 | 21 | 22 |  |  |  | 21.5 | 138.9% | Achieved | SSBB Project-Gourav Sarkar | 2026-08-10 | 1.Inser comment
41 | I | 49096 | Goutam Patel | Unit-IV | Business Excellence | Reduce the specific power Consumption of Furnace-2 per day from 4251 kWh/MT to 3700 kWh/MT of Ferro Alloys. | Decreasing | Kwh/MT | April-25 -Jan'26 | 4251 | 3700 |  | 3775.8362 | 4010.5588 | 3850.386 | 3920.7315 | 3837.6282 | 3832 |  |  | 3871.1901 | 68.93% | On Track | SSBB Project-Goutam Patel | 2026-08-10 | 1.Inser comment
9 | II | 7855 | Harsh Sharma | Unit-III | Sinter Mechanical | Reducing Down time per month from 8.77 to < 5 hr for SP1 . | Decreasing | Hrs/month | May'25-Aug'25 | 8.77 | 5 | 7.11 | 5.5 | 6.66 | 11.25 | 8.08 | 6.08 | 17.33 | 10.75 |  | 8.8586 | -2.349% | Needs Attention | SSBB Project-Harsh Sharma | 2026-08-10 | 1.Inser comment
10 | II | 7855 | Harsh Sharma | Unit-III | Sinter Mechanical | Reducing Down time per month from from 6.13 to < 3 hr for SP2. | Decreasing | Hrs/month | May'25-Aug'25 | 6.13 | 3 | 13.5 | 5.2 | 4.58 | 4.83 | 3.25 | 5.5 | 2.25 | 9.9167 |  | 5.5871 | 17.34% | Needs Attention | SSBB Project-Harsh Sharma | 2026-08-12 | 1.Inser comment 2. Issue hopper
62 | II | 7780 | Hilary Joseph | Unit-III | Industrial Relationship | Reducing Manpower cost /MT 4.58 cr from 3.67 cost/MT | Decreasing | Cost/MT | [14 empty] | No Data | SSBB Project-Hilary Joseph | 2026-08-12 | 1.Inser comment 2. Issue hopper
51 | II | 5733 | Kalyan Lahiri | Unit-III | Supply Chain Management | Increase the average service cost saving of jai Balaji Industries Ltd Unit-III per month from 17.8 Lakh to 19.58 Lakh. | Increasing | Lakh |  | 17.8 | 20 | [11 empty] | No Data | SSBB Project-Kalyan Lahiri | 2026-08-12 | 1.Inser comment 2. Issue hopper
76 | II | 3069 | Kamal Bandyopadhyay | Unit-III | Account | Reduce Avg Planned vs. Actual Cost Variation of the MBF Plantper month from 1449 to 1232. | Decreasing | [15 empty] | No Data | SSBB Project-Kamal Bandyopadhyay | 2026-08-12 | 1.Inser comment 2. Issue hopper
34 | II | 48820 | Kumar Dipendra | Unit-IV | CPP Operations | Increase Avg BFG Boiler steam Generation Per month from 31.4 TPH to > 33 TPH. | Increasing | TPH | Oct-24-Oct-25 | 31.4 | 33 | 34.5658 | 30.916 | 31.4231 | 31.47 | 31.6519 | 31.4533 | 31.597 | 31.42 |  | 31.8682 | 29.26% | Needs Attention | SSBB Project-Kumar Dipendra | 2026-08-12 | 1.Inser comment 2. Issue hopper 3. Change the Target due to low production | 2026-08-26
2 | I | 16407 | Manas Mukherjee | Unit-I | Ferro Operations | Increase the Avg Metal recovery(High SiMg) from 83.48% to 90 % for Furnace #1 | Increasing | % | Jan'25-Sept25 | 83.48 | 90 | 87.04 | 86.12 | 86.05 | 85.75 | 84.3 |  |  |  |  | 85.852 | 36.38% | Needs Attention | SSBB Project-Manas Mukherjee | 2026-08-10 | CTQ to convert Per day and Realing 2. issue hopper
78 | II | 47561 | Mohammad Ahmad | Unit-IV | Human Resource | Optimize manpower cost of Unit -IV. | Decreasing | [15 empty] | No Data | SSBB Project-Mohammad Ahmad | 2026-08-10 | 1.Issue hopper 2. Insert comment
8 | II | 6363 | Molay Pan | Unit-III | Coke Oven Electrical | Reduce Specific energy consumption per day of Coke oven plant from 9.36 KWh/Ton to < 8 KWh/Ton . | Decreasing | KWh/Ton | Jan'25 - Dec'25 | 9.36 | 8 | 7.99 | 8.38 | 8.88 | 9.46 | 9.6 | 11.14 | 10.48 | 9.63 |  | 9.4186 | -4.307% | Needs Attention | SSBB Project-Molay Pan | 2026-08-10 | 1.Issue hopper 2. Insert comment
54 | II |  | Nagendra singh | Unit-III | MBF Operation | Increase the Avg Production of MBF2 per day from 575 Ton to > 650 Ton. | Increasing | Ton/day | Mar-25-Oct-25 | 575 | 650 | 677.5161 | 677.7857 | 648.6923 | 658.8276 | 638.4706 | 632.5417 |  |  |  | 655.639 | 107.5% | Achieved | SSBB Project-Nagendra singh | 2026-08-10 | 1.Issue hopper 2. Insert comment
44 | I | 6323 | Nagesh Kumar | Unit-III | DIP Electrical | Reduce the specific power consumption of DIP Compressor from 52.83 KWH/MT to 35 KWH/MT per day. | Decreasing | Kwh/MT | Augt'25-Nov'25 | 38.75 | 35 | 20 | 23 | 24 | 29 | 28 | 25 | 29 | 31.006 | 22.756 | 25.4286 | 355.2% | Achieved | SSBB Project-Nagesh Kumar | 2026-08-10 | 1.Issue hopper 2. Insert comment
48 | II | 5612 | Nilesh Rathaur | Unit-III | Safety | Reducing Mandays loss of Jai Balaji Unit-3 from 1546 per month to 600 per /month | Decreasing | Days | Jun'24-Dec'25 | 1411 | 1000 | 1591 | 1637 | 1108 | 34 | 87 | 139 |  |  |  | 766 | 156.9% | Achieved | SSBB Project-Manoj Kumar
49 | II | 8216 | Pankaj Dubey | Unit-III | Human Resource | Reducing LWP per month from 3.10 to <2%. | Decreasing | % | Jan'25-Sep'25 | 3.1 | 2 | 0.93194 | 1.4 | 1.7 | 2.1 | 2.2 | 2.1 |  |  |  | 1.7387 | 123.8% | Achieved | SSBB Project-Pankaj Dubey | 2026-08-12 | 1.Data to be change 2. Issu hopper
35 | I | 45833 | Papan Nayak | Unit-IV | CPP Operations | Reduce the Avg Steam loss of Power Plant per month from 8895 to 2261 ton. | Decreasing | Ton/Month | Dec'24-Oct25 | 8894 | 2261 | 859 | 528 | 550 | 371 | 390 | 586 | 981 |  |  | 609.2857 | 124.9% | Achieved | SSBB Project-Papan Nayak | 2026-08-10 | 1.Issue hopper 2. Insert comment
63 | II | 9517 | PK Swain | Unit-IV | Electrical | Improving power factor from ------- to -------- in Unit -IV. | Increasing | [15 empty] | No Data | SSBB Project-PK Swain
45 | I | 10952 | Prakash Joshi | Unit-III | Human Resource | Manpower cost optimization per month from 7.04 cr to 6.8 cr of Unit-III. | Decreasing | Crore | June-25-Sept'25 | 7.04 | 6.8 | 6.41 | 6.7 | 6.9876 | 7.1283 | 7.1053 | 7.1718 | 7.1939 |  |  | 6.9567 | 34.72% | Needs Attention | SSBB Project-Prakash Joshi | 2026-08-10 | 1.Issue hopper 2. Insert comment
56 | II | 7747 | Prasanta Basu | Unit-III | ISO | Reduction of Paper Consumption through Effective IMS Internal Audits & Competence-Based Training from 27620 to < 5524. | Decreasing | Nos | Jan'23-Jan'25 | 27620 | 5524 | [11 empty] | No Data | SSBB Project-Prasanta Basu
11 | II | 7448 | Prasanta Karmakar | Unit-III | RMHS Operation | Increase the average monthly efficiency of Iron ore Washery Plant-1 from 77.25 % to >85%. | Increasing | % | Apr'25-Sept-25 | 77.25 | 85 | 95.1 | 92.24 | 87.6 | 86.11 | 96.05 | 90.87 | 79.7368 | 75.5556 |  | 89.6724 | 160.3% | Achieved | SSBB Project-Prasanta Karmakar
12 | II | 7448 | Prasanta Karmakar | Unit-III | RMHS Operation | Increase the average monthly efficiency of Iron ore Washery Plant-2 from 78.26 % to >85% | Increasing | % | Apr'25-Sept-25 | 78.26 | 85 | 91.61 | 94.07 | 95.7 | 95.96 | 96.46 | 96.48 | 96.2879 | 97.44 |  | 95.224 | 251.7% | Achieved | SSBB Project-Prasanta Karmakar | 2026-08-12 | 1.Insert comment 2 Issue hopper
77 | II |  | Prashnat Yadav | Mackeil | Estimation | To Increased PO Conversation Ratio | Increasing | [15 empty] | No Data | SSBB Project-Prashnat Yadav | 2026-08-10 | 1.Issue hopper 2. Insert comment
46 | II | 50360 | Pratip Roy | Unit-IV | Business Excellence | Reducing the average return fines of BQT plant per day from 17.76 % to < 15 %. | Decreasing | % | Oct-25 - Mar- 26 | 17.76 | 15 |  |  |  | 20.32 | 23.27 | 21.27 |  |  |  | 21.62 | -139.9% | Needs Attention | SSBB Project-Pratip Roy | 2026-08-12 | 1. All furnace
24 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 5 from 56 to 46 respectively i.e increase MTBF without increase MTTR. | Decreasing | Nos. | Nov'24-Oct'25 | 56 | 46 | 32 | 14 | 45 |  | 80 | 50 |  |  |  | 44.2 | 118% | Achieved | SSBB Project-Prithwis Bhattacharya | 2026-08-12 | 1.Insert comment 2. Issue hopper & add the project
25 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 6 from 54 to 44 respectively i.e increase MTBF without increase MTTR. | Decreasing | Nos. | Nov'24-Oct'25 | 54 | 44 | 44 | 34 | 36 | 33 | 47 | 55 |  |  |  | 41.5 | 125% | Achieved | SSBB Project-Prithwis Bhattacharya | 2026-08-10 | 1.Issue hopper 2. Insert comment
26 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 7A from 81 to 60 respectively i.e increase MTBF without increase MTTR. | Decreasing | Nos. | Nov'24-Oct'25 | 81 | 60 | 62 | 50 | 65 | 89 | 91 | 34 |  |  |  | 65.1667 | 75.4% | On Track | SSBB Project-Prithwis Bhattacharya | 2026-08-10 | 1.Issue hopper 2. Insert comment
27 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 9 from 74 to 50 respectively i.e increase MTBF without increase MTTR. | Decreasing | Nos. | Nov'24-Oct'25 | 74 | 50 | 21 | 28 | 55 | 19 | 57 | 50 |  |  |  | 38.3333 | 148.6% | Achieved | SSBB Project-Prithwis Bhattacharya
20 | II | 7313 | Pushpendra Ganguly | Unit-III | MBF Operation | Increase the Avg Productivity of MBF2 per day from 3.46 Ton/m3 to >3.606 Ton/m3 . | Increasing | Ton/day/m3 | Aug'25-Dec'25 | 3.46 | 3.606 | 3.408 | 3.395 | 3.424 | 3.5219 | 3.496 | 3.51 | 3.5513 | 3.5227 |  | 3.4723 | 8.434% | Needs Attention | SSBB Project-Pushpendra Ganguly | 2026-08-10 | 1.Issue hopper 2. Insert comment
3 | I | 4 | Ravindra Kumar Meherwal | Unit-III | Central Electrical | Increase the Avg Load factor of LCFC per month(for furnace 1 to 5) from 0.78 to 0.83. | Increasing | Load Factor | Jul'25-Oct'25 | 0.78 | 0.83 | 0.79 | 0.73 | 0.80298 | 0.77707 | 0.7919 | 0.73794 |  |  |  | 0.77165 | -16.7% | Needs Attention | SSBB Project-Ravindra Kumar Meherwal
74 | I | 10811 | Roopam Rai | HO | Business Excellence | Development of New Products with High Demand for Open Die Forgings Plant". | Increasing | [15 empty] | No Data | SSBB Project-Roopam Rai |  | 1.Over time 2.Man power requirement per ton 3.
14 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90% ( Grade - Cr-60 & C-0.50 %) in Ferro alloys division in AOD | Increasing | % | Augt'25-Dec'25 | 87 | 90 | [11 empty] | No Data | SSBB Project-Sailesh Singh Yadav
15 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90% ( Grade - Cr-60 & C-5 %) in Ferro alloys division in AOD | Increasing | % | Augt'25-Dec'25 | 88.79 | 90 |  | 86.16 | 84.35 |  |  | 83.39 | 80.25 | 86.3 |  | 83.5375 | -434.1% | Needs Attention | SSBB Project-Sailesh Singh Yadav
16 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90%( Grade - Cr-66 & C-0.75 %) in Ferro alloys division in AOD | Increasing | % | Oct'25-Dec'25 | 86.53 | 90 | 87.19 | 90.3 | 90.17 |  | 90.89 |  | 91.23 | 87.71 |  | 89.956 | 98.73% | On Track | SSBB Project-Sailesh Singh Yadav | 2026-08-10 | Project to be change
21 | I | 0 | Samanway Das | Unit-III | MBF Operation | Reduce the Fuel consumption of Blast furnace 2 per day from 613 Kg/THM to 550 Kg/THM. | Decreasing | Kg/THM | Jul'25-Dec'25 | 613 | 550 | 627.3703 | 609.0714 | 604.2667 | 596.8333 | 610.3357 | 592.0435 | 593 | 595 |  | 604.703 | 13.17% | Needs Attention | SSBB Project-Samanway Das
22 | I |  | Samanway Das | Unit-III | MBF Operation | Reduce coke Rate of Blast furnace 2 per day from 492 Kg/THM to 400 Kg/THM. | Decreasing | Kg/THM | Jul'25-Dec'25 | 492 | 400 | 528.6129 | 508.7857 | 483.5333 | 476.9667 | 488.4221 | 451.0164 | 460 | 461 |  | 485.3339 | 7.246% | Needs Attention | SSBB Project-Samanway Das | 2026-08-12 | 1.Insert comment
23 | I |  | Samanway Das | Unit-III | MBF Operation | Increase coal Injection Rate of Blast furnace 2 per day from 118 Kg/THM to 150Kg/THM. | Increasing | Kg/THM | Jul'25-Dec'25 | 118 | 150 | 98.7574 | 100.2857 | 120.7333 | 119.8667 | 121.9137 | 141.0272 | 133 | 134 |  | 119.3691 | 4.279% | Needs Attention | SSBB Project-Samanway Das
4 | I | 10818 | Sandip Sil ,A.P Sahoo,Sudipta Chatterjee,Ashish Ranjan | Unit-III | DIP Operation | Reducing over all rejection of DIP from 9.9 % to 6.90 % . | Decreasing | % | Dec'24-Oct'25 | 9.9 | 6.9 | 7.03 | 6.83 | 8.12 | 9.38 | 9.96 | 8.34 | 7.41 |  |  | 8.1529 | 58.24% | On Track | SSBB Project -Sandip Sil, Ambika Sahoo | 2026-08-12 | 1. Non conformance (External) 2.Customer complain 3.Add project
5 | I | 4939 | Sandipan Ghosh | Unit-III | RMHS Electrical | Increase the average plant availability of Iron Ore Washery from 84.48 % per day to >90% for IOW-1 . | Increasing | % | Apr'25-Oct'25 | 84.48 | 90 | 97.037 | 81.4583 | 73.8889 | 86.9231 | 86.5556 | 93.32 | 95.8333 | 76.9815 |  | 87.8595 | 61.22% | On Track | SSBB Project-Sandipan Ghosh
6 | I | 4939 | Sandipan Ghosh | Unit-III | RMHS Electrical | Increase the average plant availability of Iron Ore Washery from 81.70% per day to >90% for IOW-2. | Increasing | % | Apr'25-Oct'25 | 81.77 | 90 | 99.7222 | 95.2646 | 98.9759 | 95.6308 | 96.6111 | 99.3904 | 99.6296 | 98.5 |  | 97.8892 | 195.9% | Achieved | SSBB Project-Sandipan Ghosh |  | 1.No of Sample 2. Deviation
17 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -1 84.53 % per month 88.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 84.53 | 88 | 85.3 | 86.08 | 84.1 | 81.44 | 84.68 | 85.0383 | 82.8177 |  |  | 84.208 | -9.28% | Needs Attention | SSBB Project-Sanjay Nayak
18 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -2 80.23 % per month 85.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 80.23 | 85 | 76.27 | 84.1 | 79.73 | 83.02 | 82.88 | 90.0607 | 84.7771 |  |  | 82.9768 | 57.59% | On Track | SSBB Project-Sanjay Nayak
19 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -III 87.83 % per month 90.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 87.83 | 90 | 87.7 | 87.18 | 84.24 | 83.85 | 86.15 | 74.4617 | 88.4932 |  |  | 84.5821 | -149.7% | Needs Attention | SSBB Project-Sanjay Nayak
72 | I |  | Sanjib Pattnaik | UNIT-I | Human Resource |  | Decreasing | [15 empty] | No Data | SSBB Project-Sanjib Pattnaik
38 | II | 4837 | Sashank Shekhar | Unit-III | MBF-Mechanical | Increased Productivity of Pig Casting Machine -1 (Double Strand) | Increasing | MT/Day | 2026-06-01 00:00:00 | 572 | 800 | [11 empty] | No Data | SSBB Project-Sashank Shekhar
39 | II | 4837 | Sashank Shekhar | Unit-III | MBF-Mechanical | Increased Productivity of Pig Casting Machine -2 (Double Stand) | Increasing | MT/Day | 2026-06-01 00:00:00 | 520 | 800 | [5 empty] | 528 |  |  |  | 528 | 2.857% | Needs Attention | SSBB Project-Sashank Shekhar | 2026-08-10 | 1.Issue hopper 2. Insert comment
29 | I |  | Shantimoy Som | Unit-III | Coke Oven | Increase Avg steam of WHRB plant through coke Gas from 1480Ton/day to >1704 Ton/day . | Increasing | MT/Month | Oct24-Sep'25 | 1480 | 1704 | 1917.9871 | 1765.4918 | 1567.6714 | 1759.592 | 1889.729 | 1832.4 | 1842.929 | 1795 | 1709 | 1796.5429 | 141.3% | Achieved | SSBB Project-Shantimoy Som | 2026-08-10 | 1.Issue hopper 2. Insert comment
68 | II | 48624 | Sidheswar Biswal | Unit-IV | Safety | Reducing unsafe condition per months from 406 to < 203. | Decreasing | Nos | [14 empty] | No Data | SSBB Project-Sidheswar Biswal | 2026-08-10 | 1.Issue hopper 2. Insert comment
61 | II | 50618 | Sohel Rana | Unit-IV | Business Excellence | Breakdown reduction in rolling Mill #2 from 15.03 % to <10.0% | Decreasing | % | Oct'25-Dec'25 | 15.03 | 10 | 8.14 | 6.3 | 6.8 | 5.5 | 11.18 | 7.63 |  |  |  | 7.5917 | 147.9% | Achieved | SSBB Project-Sohel Rana | 2026-08-10 | 1.Issue hopper 2. Insert comment
28 | II | 5152 | Somnath Patra | Unit-III | Sinter Electrical | Reduce the Specific Power Consumption of Sinter Plant 1 from 52.99 kWh/MT to <45 kWh/MT per day. | Decreasing | kWh/Ton | Aug'25-Nov'25 | 52.989 | 45 | 49.72 | 61.39 | 56.93 | 49.46 | 53.22 | 57.65 | 46 |  |  | 53.4814 | -6.164% | Needs Attention | SSBB Project-Somnath Patra
| II | 5152 | Somnath Patra | Unit-III | Sinter Electrical | Production volume of sinter plant-1
71 | II | 11039 | Soumen Pal | HO | DIP Marketing | Re-establish the tendor data base (tendor missing) per month from -------to ----. | Increasing | Nos | [14 empty] | No Data | SSBB Project-Soumen Pal
70 | II | 10860 | Souptik Mondal | HO | DIP Marketing | Reducing the freight cost per Km /MT from 580 to <----. |  | Per kM/MT | [14 empty] | No Data | SSBB Project-Souptik Mondal
75 | II | 3927 | Subhash Ghosh | Unit-III | Civil | Vendor cost optimization | Decreasing | [15 empty] | No Data | SSBB Project-Subhash Ghosh
30 | I |  | Sugyan Dora | Unit-IV | DRI | Improve the Avg Productivity of Kiln per day 3.83 ton/hr to 4 ton/hr for Kiln#1 | Increasing | MT/Hr | Sep'25-Dec'25 | 3.83 | 4 | 3.96 | 3.96 | 3.74 | 3.76 | 3.83 | 3.8 | 3.83 |  |  | 3.84 | 5.882% | Needs Attention | SSBB Project-Sugyan Dora
31 | I |  | Sugyan Dora | Unit-IV | DRI | Improve the Avg Productivity of Kiln per day 3.90 ton/hr to 4 ton/hr for Kiln#2 | Increasing | MT/Hr | Sep'25-Dec'25 | 3.9 | 4 | 3.9 | 3.97 | 3.88 | 3.84 | 3.88 | 3.89 | 3.39 |  |  | 3.8214 | -78.57% | Needs Attention | SSBB Project-Sugyan Dora
32 | I |  | Sugyan Dora | Unit-IV | DRI | Improve the Avg Productivity of Kiln per day 3.76 ton/hr to 4 ton/hr for Kiln#3 | Increasing | MT/Hr | Sep'25-Dec'25 | 3.76 | 4 | 3.38 | 3.86 | 3.68 | 2.95 | 4.09 | 3.97 | 3.84 |  |  | 3.6814 | -32.74% | Needs Attention | SSBB Project-Sugyan Dora
33 | I |  | Sugyan Dora | Unit-IV | DRI | Improve the Avg Productivity of Kiln per day 3.63 ton/hr to 4 ton/hr for Kiln#4 | Increasing | MT/Hr | Sep'25-Dec'25 | 3.63 | 4 | 3.65 | 3.53 | 3.89 | 2.8 | 4.04 | 4.07 | 3.58 |  |  | 3.6514 | 5.792% | Needs Attention | SSBB Project-Sugyan Dora
58 | II | 30103 | Suman Majumder | JSBIL | Operation (Chemist) | Reduce the Laboratory Operational cost per heat per day from 1392 to <1100. | Decreasing | INR/Heat | Nov'25-Dec'25 | 1392 | 1100 | 1348.3 | 1148.71 | 1159.25 | 1085.74 | 1072.2 | 1067.87 | 1100 | 1044.5 |  | 1140.2957 | 86.2% | On Track | SSBB Project-Suman Majumder
42 | II | 3413 | Surajit Thakur | Unit-III | Electrical | Reduce Power Consumption per Heat of Furnace-2 from 6951 kWh to <6700 kWh in LCFC Plant. | Decreasing | kWh/Heat | Oct'25-Dec'25 | 6951 | 6700 | 6845 | 6963 | 6703 | 6664 | 6647 | 6635 |  |  |  | 6742.8333 | 82.93% | On Track | SSBB Project-Surajit Thakur
Legend: | Achieved | On Track | Needs Attention
Note: 'Average (Actual)' = mean of Jan-Jun actuals entered. 'Progress %' compares Average vs Target relative to Baseline, direction-aware (Increasing/Decreasing). Source: Master Data sheet, 15projects_SSBB_Final.xlsx (Jan–Jun 2026 tracking).
Note on M22: 1. Ash will be linearly 2 Reduce the contamination of Caol 3. Optimization of Blending ratio
Note on S25: Taken median after removing 5 outliers and p<0.05
Note on T25: p<0.05, taken median and removed 2 outliers
Note on P28: 1. Required work will be completed in Up-coming capital shutdown.
Note on N33: 1. MBF shutdown
Note on Q33: 1. MBF shutdown
Note on R33: 1.MBF shutdown
Note on M36: 1. Caol quality change
Note on R36: 1.Raining Season last year compared
Note on K37: 1. Alignment issue Prime
Note on K45: 1. Low screening efficiency 2.low washing efficiency 3. feeding arrangment not working properly 4.
Note on M45: 1.
Note on N45: 1.
Note on M53: 1.Capital repairing delay by one month 2. this delay worsen the productivity
Note on N53: 1.Capital repairing 2.
Note on T53: After removing 3 outliers
Note on T83: P-Value < 0.05
Note on O84: 1.Main power off during charging but now power will be off at the time electro replacement.

## Sheet2 (hidden)
B | Product
B1 | Mould
B11 | industrial sectior
B11.1 | DI pipe industries
| Sizes (mm) | DN 100 to 350
| Length(mm) | 5.5
B2 | Ring Forging
B2.1 | industrial sectior
Wind energy
Heavy Machinaries

## Maintenance (hidden)
P | Maintain A Machine
P1 | Select Machine
P2 | Install & commision the Machine
P3 | Use the Machine
P4 | Maintain the Machine
P5 | Assess the Helth of the Machine
P6 | Modify the machine

## DCP-Conpilation (hidden)
T2 | T1 | C1 | X1 | Y | Z1 | Z2 | Z3 | Z3.1
Month | Date | Day | Volume of Product | % Absentism | inventory volume | Rejection | Financial | Over time
Note on B3: Time oriented causal variable
Note on C3: Categorical causal variable
Note on D3: Numeric Cause
Note on E3: Target Variable
Note on F3: Consequent variable

## DCP-Collection (hidden)
T1 | T2 | T3 | C1 | X21 | X22 | X3 | I1 | I1' | I2 | X1 | U1 | Y-Micro | Y | Z1 | Z2 | Z3 | Z3.1
Month | Date | Shift | Day | No of Labourer |  | Labours | Role No | Name | Gender | Volume of Product(MT) | Cause for Absentism | Absent-1 Present-0 | % Absentism | inventory volume | Rejection | Financial | Over time
|  |  |  | Plan | Actual
2026-08-01 | 2
|  | A | Mon | 120 | 100 |  |  |  |  | 125 |  |  | 16.67%
[6 empty] | L1 | [5 empty] | 0
0
1
0
0
0
2026-08-01 | 2 | B | Mon
Note on B2: Time oriented causal variable
Note on D2: Categorical causal variable
Note on H2: identification no
Note on K2: Numeric Cause
Note on N2: Target Variable
Note on O2: Consequent variable

## Quality-DCP (hidden)
Supplier | R&D
Input | Requiremnts of mining
Code | P | P1 | P2 | P3 | P4 | P5 | P6
Process | Mining Mgmt | Identify the sources | select the source | Communicate the requirement of vendor of the source | Materialized or crytalized | Generic /Special/ requirement
Resource | Lab
Output | Test Result
Customer | Pdn / Comm / Mgmt
CODE | T1 | I1 | C1 | C2 | C3 | C4 | X1 | Y1 | Y11 | Y12 | Y13 | Y14 | Y15 | Y16 | Y17 | Y18 | Y2 | Y21 | Y22 | Y23 | Y24 | U1
CTQ --> | Date | Iron ores | Batch | Mines | Sampler | Type of Product | Sample Qty | Chemical properties | T-Fe | SiO2 | Al2O3 | P | Mn | TiO2 | Cr | Zn | Physical properties | Moisture | Oversize | Undersize | Tumbler Index | Remark
DCP
Description
Type of Data
UOM
Type of Spec
USL
TARGET
LSL
Minimum Frequency of Data
Data Source
Resposibility
Reaction Plan or Troubleshooting checklist
SOP
Measurement Support System
Instruments / Measurement Device / Test Method
Make of the Instrument
Age of the Instrument
Credibility of the Instrument
Accuracy
Least Count
Bias
Calibration SOP
LC of Calibrator
Agreement %
KAPPA Value
Precision of Instru
Sigma R&R
Comment on Accuracy
Note on A15: Higher the better Lower the better Target is the best Unstructured Data

## DFSS (hidden)
1 | Inroducing DFSS
1.01 | New product
1.02 | New service
1.03 | New process
1.03.01 | Manufacturing process
1.03.02 | Service provision
1.04 | New system
1.05 | New Software
1.06 | New competency
2 | MGAP for company
2.01 | MGMT(Multigeneration market trends)
2.02 | MGPP(Multigeneration product Plan)
2.03 | MGPP(Multigeneration Process Plan)
2.04 | MGTP(Multigeneration Technology platform
2.04.01 | Product Technology
2.04.02 | Process Technology
2.05 | Critical Assumptions
3 | Type of New
3.01 | New to the world
3.02 | New to the Company
3.03 | New to the product family
3.04 | New to the product line
3.05 | New to the Brand of the same product line for the same product family
3.06 | Same product with more alternative application
3.07 | Same product with reduced cost
3.08 | New product with small-small added features
4 | DFSS issue hopper
5 | Define phase of DFSS
6 | Project charter
7 | Surrogate Selection | For Surrogate |  | Representative person or premises | Additional expectation of new product | Risk | Requirement
8 | Product life cycle member identification | Strength | weakness
8.01 | TLC (Technology life cycle) Members
8.01.01 | Induction Hardening
8.01.02
8.01.03
8.01.04
8.02 | DLC (Design life Cycle ) Members
8.02.01
8.02.02
8.02.03
8.03 | In Bound Supply chain-Sourcing , input ,requirement or concerns
8.04 | Manufacturer -Received of Raw material to storage of Finished goods
8.05 | Manufacturer to Customer-out bound supply chain-logistics
8.05.01 | Finished goods stores
8.05.02 | Packaging
8.05.02.01 | Primary
8.05.02.02 | Secondary
8.05.02.03 | Tertiary
8.05.02.04 | Cargo
8.05.02.05 | Loading
8.05.02.06 | Unloading
8.05.03 | Transport
8.05.03.01 | Surface
8.05.03.01.01 | Truck
8.05.03.01.02 | Freight insurance
8.05.03.01.03 | Road
8.05.03.01.04 | Rail
8.05.03.02 | water
8.05.03.02.01 | Ship
8.05.03.02.02 | Container
8.05.03.02.03 | Custom Clearance agency
8.05.03.03 | Air
8.05.03.03.01 | Air line
8.05.03.03.02 | Agent
8.05.03.03.03 | Cargo
8.05.03.03.04 | Custom Clearance agency
8.05.03.04 | Combination of all
8.05.04 | Unloading
8.05.05 | Storage at customer place
8.05.06 | Ducoment or information out bound supply chain
8.05.07 | Governments Law for out bound
8.06 | Product in field with customers | Representative person |  | E-mail address | Mob. No | Concern | Requirement
8.06.01 | Product used environment
8.06.02 | who take the decision to purchase the product from customer family
8.06.03 | A member of a Customer family to take a decision how the product deliver to customer facility
8.06.04 | Who used the product
8.06.05 | How to product to be Maintain
8.06.06 | spare part for maintain
8.06.07 | Servicing
8.07 | Disposition of product against Suffocation & Proposition of Customer & Government Condition
8.07.01 | Customer
8.07.01.01 | Resale value
8.07.01.02 | Re-cycle
8.07.02 | Government
8.07.02.01 | Legality of disposition
9 | VoS & Risk mitigation plan
10 | ER Layer
11 | E -CTQ Dashboard
12
13
14
15
16
1 | Marketing
2 | sales
3 | Orders
4 | R&D if Required
5 | Expand capacity
6 | Product design
7 | Planning
7.01 | Plan for RM (In bound supply chain)
7.01 | Man power
7.01 | Machine
7.01 | Utility
7.01 | Method
8 | Full fill the Order
8.01 | Produce
8.02 | Service provision
8.03 | Finance , Product & Services
9 | Deliver order
9.01 | Prodcut at customer End
10 | Collect Money
11 | Used of the product at Customer
12 | Customer feedback
13 | Support services
13.01 | Specific Support services
13.01.01 | RM, Manpower, Machine,Method, Utility
13.02 | Generic support Services-
13.02.01 | Corporate
13.02.02 | HR
13.02.03 | Information Management system
13.02.04 | Finance
13.02.05 | Account
13.02.06 | SHE& F
13.02.07 | legal
13.02.08 | IMS

## MGPP (hidden)
[33 empty] | short term |  | Mid term | Long term
[32 empty] | Current year | ABP |  | SBP | MGP
|  |  |  | 1998-99 | 1999-2000 | 2000-2001 | 2001-2002 | 2002-2003 | 2003-2004 | 2004-2005 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40
A | Product |  | UOM
M | Market
M01 | No of Customers
M02 | Market share (%)
M03 | No of Competitors
M03.01 | Competitor-1
M03.02 | Competitor-2
M03.03 | Competitor-3
M03.04 | Competitor-4
M04 | Avg Revenue Per unit of Customer per year
M05 | Revenue
M06 | Investment
M07 | Profits
M08 | Tax
M09 | No of patent
A01 | DIP
A01.01 | DI pipe | Volume | MT
|  | Value | Cr.
A01.02 | PIG iron | Volume | MT
|  | Value | Cr.
A02 | Ferro Alloys
A02.01 | LCFC | Volume | MT
|  | Value | Cr.
A02.02 | MCFC | Volume | MT
|  | Value | Cr.
A04 | TMT Bar | Volume | MT
|  | Value | Cr.
A05 | DRI | Volume | MT
|  | Value | Cr.
| Billets | Volume | MT
|  | Value | Cr.
| Nail | Volume | MT
|  | Value | Cr.
| Coke | Volume | MT
|  | Value | Cr.
| MS rod | Volume | MT
|  | Value | Cr.
| OPVC | `
By Product
G- slag
Hopper slag
Runner scrap
Rejection pipe
B | Process
B01 | Unit-I | Capacity
Volume
B02 | Unit-II | Capacity
Volume
B03 | Unit-III | Capacity
Volume
B04 | Unit-IV | Capacity
Volume
B05 | Unit-V | Capacity
Volume
C | Technology Platform
C01 | Product Technology
C02 | Process Technology
D | Critical Assumption
New-Double chamber Restraint Joint
Surrogate product
Single chamber Restraint joint
Socket spigot Push on joint
Note on B5: Multigeneration Product plan
Note on B53: Multigeneration process Plan
Note on B64: Multigeneration Technology platform
Note on B69: 1. Iner & outer profile differ but gasket profile same
Note on B71: 1. Internal profile of socket & gasket design will be same with socket spigot push on joint only outer profile of the socket will differ

## MGAP (hidden)
[10 empty] | Short term |  |  |  | Mid term |  | Long term
|  |  |  | 2024-25 |  | 2025-26 |  | 2026-27 |  | 2027-28 |  | 2028-29 |  | 2029-30 |  | 2030-35 |  | 2035-40 |  | 2040-50
[8 empty] | Current year |  | ABP (Annual Business plan) |  |  |  | SBP(strategic Business plan) |  | MGP(Multigenration plan)
|  |  | UOM | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan
A | Market
A.01 | Customer
A.01.01 | No of Customer
A.01.02 | ARPU(Avg Revenue of per unit of per Customers per year
A.02 | Finance
A.02.01 | Revenue
A.02.02 | Expenditure
A.02.03 | Tax
A.03 | Competitors
A.03.01 | No of Competitors
A.03.01A | Competitor 1------
A.03.02 | Market share of all competitors
A.04 | Government
A.04.01 | IPR
A.04.01.01 | Trade mark
A.04.01.02 | Copy right
A.04.01.03 | Paper
A.04.01.04 | Patent
A.04.02 | Municipality law
A.04.03 | State law
A.04.04 | Central law
A.04.05 | Importing country law
A.04.06 | Exporting country law
A.04.07 | Labours law
A.04.08 | Company Act
B | Product
B1 | DI pipe | Volume | MT | 400000 | 500000 | 150000 | 200000 | 200000 | 300000 |  | 550000 |  | 550000
|  | value | cr | 2000 | 2500 | 750 | 1000 | 1000 | 1500 |  | 2750 |  | 2750
B1.01
B1.02
B1.03
B1.04
B1.05
B1.06
B1.07
B1.08
B1.09
B1.10
B1.11
B1.12
B1.13
B1.14
B1.15
B1.16
B1.17
B2 | PIG iron | Volume
value
B3 | LCFC | Volume
value
B4 | By product | Volume
value
B4.01 | Runner Scrap | Volume
value
B4.02 | DI Slag | Volume
value
B4.03 | Rejected pipe | Volume
value
B4.04 | Granulated slag | Volume
value
B4.05 | Slag bolder | Volume
value
B4.06 | Runner dust | Volume
value
B4.07 | Core sand | Volume
value
B4.08 | Zn Cut wire & dust | Volume
value
B4.09 | Cutting DI pipe dust | Volume
value
B4.10 | BF Gas | Volume
value
C | Process
C.01 | Unit-III
C.01-01 | Capacity
C.01-02
C.02
C.03
Note on J33: 1.No midle east war 2.Goverment will released plan found 3. 15 % Export plan 4.

## Sheet1 (hidden)
SIX SIGMA / SSBB PROJECT TRACKING SHEET
Participants ¦ Project Theme ¦ Baseline Period, UOM & Data ¦ Target ¦ Monthly Tracking (Jan–Jun) ¦ Location & Department
PROJECT & PARTICIPANT INFO | [6 empty] | PROJECT TYPE |  |  | BASELINE & TARGET |  | MONTH-WISE ACTUAL TRACKING (JAN – JUN) | [5 empty] | PERFORMANCE SUMMARY
S.No | Batch | Employee Code | Participant's Name | Location / Unit | Department | Project Theme / Title | Improvement Direction | Baseline UOM | Baseline Period | Baseline Data | Target | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Average (Actual) | Progress % | Status
5 | I |  | Sandip Sil ,A.P Sahoo,Sudipta Chatterjee,Ashish Ranjan | Unit-III | DIP Operation | Reducing over all rejection of DIP from 9.8 to 6.8 % for K9. | Decreasing | % | Dec'24-Oct'25 | 9.8 | 6.8 | 4.41 | 4.02 | 5.98 | 5.49 | 7.28 | 4.21 | 5.2317 | 152.3% | Achieved
7 |  |  | Sandipan Ghosh | Unit-III | RMHS Electrical | Increase the average plant availability of Iron Ore Washery from 81.70% per day to >90% for IOW-2. | Increasing | % | Apr'25-Oct'25 | 81.77 | 90 | 96.3 | 95.2646 | 96.3 | 95.6308 | 95.37 | 96.15 | 95.8359 | 170.9% | Achieved
12 | II | 7448 | Prasanta Karmakar | Unit-III | RMHS Operation | Increase the average monthly efficiency of Iron ore Washery Plant-1 from 77.25 % to >85%. | Increasing | % | Apr'25-Sept-25 | 77.25 | 85 | 95.1 | 92.24 | 87.6 | 86.11 | 96.05 | 90.87 | 91.3283 | 181.7% | Achieved
13 | II | 7448 | Prasanta Karmakar | Unit-III | RMHS Operation | Increase the average monthly efficiency of Iron ore Washery Plant-2 from 78.26 % to >85% | Increasing | % | Apr'25-Sept-25 | 78.26 | 85 | 91.61 | 94.07 | 95.7 | 95.96 | 96.46 | 97.61 | 95.235 | 251.9% | Achieved
25 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 5 from 58 to 46 respectively i.e increase MTBF without increase MTTR. | Decresing | Nos. | Nov'24-Oct'25 | 56 | 46 | 32 | 14 | 45 |  | 80 | 50 | 44.2 | 118% | Achieved
26 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 6 from 55 to 44 respectively i.e increase MTBF without increase MTTR. | Decresing | Nos. | Nov'24-Oct'25 | 54 | 44 | 44 | 34 | 36 | 33 | 47 | 55 | 41.5 | 125% | Achieved
28 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 9 from 63 to 50 respectively i.e increase MTBF without increase MTTR. | Decresing | Nos. | Nov'24-Oct'25 | 74 | 50 | 21 | 28 | 55 | 19 | 57 | 50 | 38.3333 | 148.6% | Achieved
36 | I | 45833 | Papan Nayak | Unit-IV | CPP Operations | Reduce the Avg Steam loss of Power Plant per month from 8895 to 2261 ton. | Increasing | Ton/Month | Dec'24-Oct25 | 8894 | 2261 | 859 | 528 | 550 | 371 | 390 | 586 | 547.3333 | 125.8% | Achieved
42 | II | 2483 | B.K Mishra | Unit-III | Coke Oven Operation | Reduce the Ash % in Coke of Coke oven plant per month from 12.84 to <12.5 . | Decresing | % | Jul'25-Dec'25 | 12.92 | 12.5 | 12.1 | 12.42 | 12.74 | 12.44 | 12.56 | 12.01 | 12.3783 | 129% | Achieved
45 | II | 6095 | Biswanath Banerjee | Unit-III | Drawings and Design | Reduce the Invisible Zn losses of DIP per day from 41.03 gram/m2 to 12.0gram/m2 . | Decresing | Gram/m2 | Jul'25-Oct'25 | 41.13 | 12 | 11.35 | 11.59 | 9.8 | 13.36 | 14.36 | 10.49 | 11.825 | 100.6% | Achieved
46 | I | 6323 | Nagesh Kumar | Unit-III | DIP Electrical | Reduce the specific power consumption of DIP Compressor from 52.83 KWH/MT to 35 KWH/MT per day. | Decresing | Kwh/MT | Augt'25-Nov'25 | 38.75 | 35 | 20 | 23 | 24 | 29 | 28 | 25 | 24.8333 | 371.1% | Achieved
49 | I | 48356 | Gourav Sarkar | Unit-IV | BE -RM Operation | Reduce Average Specific Power Consumption of Induction Heater Per Day from 41 to 25. | Decresing | Kwh/MT | Sep'25-Dec'25 | 34 | 25 | 22 | 22 | 22 | 20 | 21 | 22 | 21.5 | 138.9% | Achieved
51 | II | 8216 | Pankaj Dubey | Unit-III | Human Resource | Reducing LWP per month from 3.094 to <2%. | Decresing | % | Jan'25-Sep'25 | 3.1 | 2 | 0.93194 | 1.4 | 1.7 | 2.1 | 2.2 | 2.1 | 1.7387 | 123.8% | Achieved
63 | II | 50618 | Sohel Rana | Unit-IV | Business Excellence | Breakdown reduction in rolling Mill #2 from 15.03 % to <10.0% | Decresing | % | Oct'25-Dec'25 | 15.03 | 10 | 8.14 | 6.3 | 6.8 | 5.5 | 11.18 | 7.63 | 7.5917 | 147.9% | Achieved
17 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90%( Grade - Cr-66 & C-0.75 %) in Ferro alloys division in AOD | Increasing | % | Oct'25-Dec'25 | 86.53 | 90 | 87.19 | 90.3 | 90.17 |  | 90.89 |  | 89.6375 | 89.55% | On Track
19 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -2 80.23 % per month 85.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 80.23 | 85 | 76.27 | 84.1 | 79.73 | 83.02 | 82.88 | 90.0607 | 82.6768 | 51.3% | On Track
21 | II | 7313 | Pushpendra Ganguly | Unit-III | MBF Operation | Increase the Avg Productivity of MBF2 per day from 3.01 Ton/m3 to >3.606 Ton/m3 . | Increasing | Ton/day/m3 | Jul'25-Oct'25 | 3.01 | 3.6 | 3.31 | 3.25 | 3.41 | 3.47 | 3.38 | 3.5 | 3.3867 | 63.84% | On Track
27 | II | 4382 | Prithwis Bhattacharya | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month in M/C 7A from 75 to 60 respectively i.e increase MTBF without increase MTTR. | Decresing | Nos. | Nov'24-Oct'25 | 81 | 60 | 62 | 50 | 65 | 89 | 91 | 34 | 65.1667 | 75.4% | On Track
30 | I |  | Shantimoy Som | Unit-III | Coke Oven | Increase Avg steam of WHRB plant from 44958 Ton/Month to 53949 Ton/Month . | Increasing | MT/Month | Oct24-Sep'25 | 44958 | 53949 | 59458 | 49434 | 41040 | 52788 | 58582 | 54972 | 52712.3333 | 86.25% | On Track
43 | I | 49096 | Goutam Patel | Unit-IV | Business Excellence | Reduce the specific power Consumption of Furnace-2 per day from 4251 kWh/MT to 3700 kWh/MT of Ferro Alloys. | Decresing | Kwh/MT | April-25 -Jan'26 | 4251 | 3700 |  | 3775.8362 | 4010.5588 | 3850.386 | 3920.7315 | 3837.6282 | 3879.0281 | 67.51% | On Track
44 | II | 3413 | Surajit Thakur | Unit-III | Electrical | Reduce Power Consumption per Heat of Furnace-2 from 6951 kWh to <6700 kWh in LCFC Plant. | Decresing | kWh/Heat | Oct'25-Dec'25 | 6951 | 6700 | 6845 | 6963 | 6703 | 6664 | 6647 | 6635 | 6742.8333 | 82.93% | On Track
47 | I | 10952 | Prakash Joshi | Unit-III | Human Resource | Manpower cost optimization per month from 7.04 cr to 6.8 cr of Unit-III. | Decresing | Crore | June-25-Sept'25 | 7.04 | 6.8 | 6.41 | 6.7 | 6.98 | 7.12 | 7.1 |  | 6.862 | 74.17% | On Track
50 | II | 5612 | Manoj Kumar | Unit-III | Safety | Reducing Mandays loss of Jai Balaji Unit-3 from 1546 per month to 600 per /month | Decresing | Days | Jun'24-Dec'25 | 1591 | 600 | 1637 | 1108 | 77 | 84 |  |  | 726.5 | 87.24% | On Track
1 | I | 16923 | Akram Imran | Unit-I | Operations | Improve the Avg Productivity of Kiln per Month from 37.42 ton to 43 ton for Kiln#1 | Increasing | TPD | Dec'24 -Sept'25 | 37.42 | 43 | 28.76 | 42.01 | 30.72 | 42.75 | 39.4231 | 42.6667 | 37.7216 | 5.405% | Needs Attention
2 | I | 16407 | Manas Mukherjee | Unit-I | Ferro Operations | Increase the Avg Metal recovery(High SiMg) from 83.48% to 90 % for Furnace #1 | Increasing | % | Jan'25-Sept25 | 83.48 | 90 | 84.26 | 82.75 |  |  |  |  | 83.505 | 0.3834% | Needs Attention
3 | I | 4 | Ravindra Kumar Meherwal | Unit-III | Central Electrical | Increase the Avg Load factor of LCFC per month(for furnace 1 to 5) from 0.78 to 0.83. | Increasing | Load Factor | Jul'25-Oct'25 | 0.78 | 0.83 | 0.79 | 0.73 | 0.80298 | 0.77707 | 0.7919 | 0.73794 | 0.77165 | -16.7% | Needs Attention
4 | I | 10818 | Sandip Sil ,A.P Sahoo,Sudipta Chatterjee,Ashish Ranjan | Unit-III | DIP Operation | Reducing over all rejection of DIP from 12.7 % to 9.7 % .for K7 . | Decreasing | % | Dec'24-Oct'25 | 12.7 | 9.7 | 9.65 | 9.64 | 10.26 | 13.26 | 13.84 | 12.47 | 11.52 | 39.33% | Needs Attention
6 | I | 4939 | Sandipan Ghosh | Unit-III | RMHS Electrical | Increase the average plant availability of Iron Ore Washery from 84.48 % per day to >90% for IOW-1 . | Increasing | % | Apr'25-Oct'25 | 84.48 | 90 | 97.037 | 81.4583 | 73.8889 | 86.9231 | 86.5556 | 93.32 | 86.5305 | 37.15% | Needs Attention
8 | I | 464 | Binoy Kumar Vishwakarma | Unit-III | Sinter Operation | Reduce the specific energy consumption per ton of sinter from 299887 to <284652 Kcal/TS. | Decreasing | % | Jan'25-Dec'25 | 299634 | 284652 | 308018.8 | 384278.8 | 345679.5 | 309111.7 | 266104 | 255905.3 | 311516.35 | -79.31% | Needs Attention
9 | II | 6363 | Molay Pan | Unit-III | Coke Oven Electrical | Reduce Specific energy consumption per day of Coke oven plant from 9.36 KWh/Ton to < 8 KWh/Ton . | Decreasing | KWh/Ton | Jan'25 - Dec'25 | 9.36 | 8 | 7.99 | 8.38 | 8.88 | 9.46 | 9.6 | 11.14 | 9.2417 | 8.701% | Needs Attention
10 | II | 7855 | Harsh Sharma | Unit-III | Sinter Mechanical | Reducing Down time per month from 8.77 to < 5 hr for SP1 . | Decreasing | Hrs/month | May'25-Aug'25 | 8.77 | 5 | 7.11 | 5.5 | 6.66 | 11.25 | 8.08 | 6.08 | 7.4467 | 35.1% | Needs Attention
11 | II | 7855 | Harsh Sharma | Unit-III | Sinter Mechanical | Reducing Down time per month from from 6.13 to < 3 hr for SP2. | Decresing | Hrs/month | May'25-Aug'25 | 6.13 | 3 | 13.5 | 5.2 | 4.58 | 4.83 | 3.25 | 5.16 | 6.0867 | 1.384% | Needs Attention
16 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90% ( Grade - Cr-60 & C-5 %) in Ferro alloys division in AOD | Increasing | % | Augt'25-Dec'25 | 88.79 | 90 |  | 86.16 | 84.35 |  |  | 83.39 | 84.6333 | -343.5% | Needs Attention
18 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -1 84.93 % per month 88.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 84.93 | 88 | 85.3 | 86.08 | 84.1 | 81.44 | 84.68 | 85.0383 | 84.4397 | -15.97% | Needs Attention
20 | I | 49269 | Sanjay Nayak | Unit-IV | Ferro Operations | Average the Cr recovery of Furnace -III 87.83 % per month 90.0 % per Month | Increasing | % | Sept'25 - Dec'25 | 87.83 | 90 | 87.7 | 87.18 | 84.24 | 83.85 | 86.15 | 74.4617 | 83.9303 | -179.7% | Needs Attention
22 | I | 0 | Samanway Das | Unit-III | MBF Operation | Reduce the Fuel consumption of Blast furnace 2 per day from 607 Kg/THM to 550 Kg/THM. | Decresing | Kg/THM | Jul'25-Oct'25 | 628 | 550 | 627 | 629 | 615 | 597 | 610 | 592 | 611.6667 | 20.94% | Needs Attention
23 | I |  | Samanway Das | Unit-III | MBF Operation | Reduce coke Rate of Blast furnace 2 per day from ---- Kg/THM to ---- Kg/THM. | Decresing | Kg/THM | Jul'25-Oct'25 | 491 | 450 | 529 | 546 | 499 | 477 | 493 | 451 | 499.1667 | -19.92% | Needs Attention
24 | I |  | Samanway Das | Unit-III | MBF Operation | Reduce coal Injection Rate of Blast furnace 2 per day from ---- Kg/THM to ---- Kg/THM. | Decresing | Kg/THM | Jul'25-Oct'25 | 118 | 100 | 98.75 | 82.58 | 120.73 | 119.86 | 118 | 141 | 113.4867 | 25.07% | Needs Attention
29 | II | 5152 | Somnath Patra | Unit-III | Sinter Electrical | Reduce the Specific Power Consumption of Sinter Plant 1 from 61kWh/MT to <45 kWh/MT per day. | Decresing | kWh/Ton | Aug'25-Nov'25 | 52.989 | 45 | 49.72 | 61.39 | 56.93 | 49.46 | 53.22 | 57.65 | 54.7283 | -21.77% | Needs Attention
31 | I |  | Sugyan Dora | Unit-IV | DRI | Productivity Improvement by enhancing Kilen#1 | Increasing | MT/Hr | Sep'25-Dec'25 | 3.83 | 4 | 3.96 | 3.96 | 3.74 | 3.76 | 3.83 | 3.8 | 3.8417 | 6.863% | Needs Attention
32 | I |  | Sugyan Dora | Unit-IV | DRI | Productivity Improvement by enhancing Kilen#II | Increasing | MT/Hr | Sep'25-Dec'25 | 3.9 | 4 | 3.9 | 3.97 | 3.88 | 3.84 | 3.88 | 3.89 | 3.8933 | -6.667% | Needs Attention
33 | I |  | Sugyan Dora | Unit-IV | DRI | Productivity Improvement by enhancing Kilen#III | Increasing | MT/Hr | Sep'25-Dec'25 | 3.76 | 4 | 3.38 | 3.86 | 3.68 | 2.95 | 4.09 | 3.97 | 3.655 | -43.75% | Needs Attention
34 | I |  | Sugyan Dora | Unit-IV | DRI | Productivity Improvement by enhancing Kilen#IV | Increasing | MT/Hr | Sep'25-Dec'25 | 3.63 | 4 | 3.65 | 3.53 | 3.89 | 2.8 | 4.04 | 4.07 | 3.6633 | 9.009% | Needs Attention
35 | II | 48820 | Kumar Dipendra | Unit-IV | CPP Operations | Increasing Steam Generation in BF Gas Boiler(free fuel Based) from 21138 Ton/Month to > 24520 Ton/Month | Increasing | Ton/Month | Mar-25-Oct-25 | 22645 | 24520 | 22848 | 11779 | 20425 | 21966 | 19276 | 18872 | 19194.3333 | -184% | Needs Attention
37 | II | 0 | Arijit Mondal | Unit-IV | CPP Operations | Increase the Steam Generation rate of 85 TPH Boiler per month from 49 to 76 ton/hrs. | Increasing | Ton/hrs | Jan-25-Nov-25 | 31048 | 54720 | 26349 | 38713 | 51859 | 37485 | 40115 | 36362 | 38480.5 | 31.4% | Needs Attention
38 | I | 45143 | Arun Thatoi | Unit-IV | Central Electrical | Increase Average Load Factor of Unit-IV from 72.49 % to >80 % per Day | Increasing | % | Aug'25-Dec'25 | 72.49 | 80 | 71.28 | 74.85 | 74.86 | 78.85 | 73.82 | 70.31 | 73.995 | 20.04% | Needs Attention
54 | I | 4781 | Anupam Basak | Unit-III | Quality | To reduce the Avg Variation of Basicity of Sinter Plant 1 from 0.08 to 0.04 . | Decresing | 0 | Aug'25-Oct'25 | 0.1018 | 0.04 | 0.99 | 0.106 | 0.105 | 0.106 | 0.102 | 0.097 | 0.251 | -241.4% | Needs Attention
55 | I | 80428 | Atish Gupta | Mackeil | Sales & Marketing | Improve on time Delivery of Finished Goods in Mackeil per month from 43 to 56%. | Increasing | % | Apr'25-Sep'25 | 43 | 56 | 41.7229 | 49.8789 | 36.9037 |  |  |  | 42.8352 | -1.268% | Needs Attention
56 | II |  | Nagendra singh | Unit-III | MBF Operation | Increase the Avg Productivity of MBF2 per day from 2.32 Ton/m3 to >3.606 Ton/m3 . | Increasing | Ton/m3 | Jul'25-Dec'25 | 2.32 | 3.6 | 2.71 | 2.72 | 2.48 | 2.54 | 2.08 | 2.07 | 2.4333 | 8.854% | Needs Attention
67 | II | 49844 | Ashutosh Pathak | Unit-IV | BE -DRI Operation | Reduced Diesal Consumption from 5.60 Ltr/Hrs to 5.0 Ltr/Hr | Decresing | Ltr/Hrs | Jul'25-Dec'25 | 4.13 | 4 | 5.36 | 4.54 | 4.83 | 4.82 | 4.72 |  | 4.854 | -556.9% | Needs Attention
14 | II | 5503 | Alok Mandal | Unit-III | Operation | Reduce the average Gox Venting Loss per month from 339 to 180 MT. | Decresing | [12 empty] | No Data
15 | II | 48956 | Sailesh Singh Yadav | Unit-IV | Operation | Cr Recovery from 87 % to > 90% ( Grade - Cr-60 & C-0.50 %) in Ferro alloys division in AOD | Increasing | % | Augt'25-Dec'25 |  | 90 | [8 empty] | No Data
39 | II |  | Sashank Shekhar | Unit-III | MBF-Mechanical | Increased Productivity of Pig Casting Machine -1 (Double Strand) | Increasing | MT/Day | 2026-06-01 00:00:00 | 572 | 800 | [8 empty] | No Data
40 | II |  | Sashank Shekhar | Unit-III | MBF-Mechanical | Increased Productivity of Pig Casting Machine -2 (Double Stand) | Increasing | MT/Day | 2026-06-01 00:00:00 | 520 | 800 | [8 empty] | No Data
48 | II | 50360 | Pratip Roy | Unit-IV | Business Excellence | Reducing feeding variance from ------ to -------for yeild improvement . | Decresing | % | [11 empty] | No Data
52 | II | 2954 | Amit Dahari | Unit-III | MBF Electrical | Reduce the Avg Specific energy consumption of MBF per month from 134.4 kWH/THM to 125 KWH/THM. | Decresing | KWH/THM |  | 134.4 | 125 | [8 empty] | No Data
53 | II | 5733 | Kalyan Lahiri | Unit-III | Supply Chain Management | Increase the average service cost saving of jai Balaji Industries Ltd Unit-III per month from 17.8 Lakh to 19.58 Lakh. | Increasing | Lakh |  | 17.8 | 20 | [8 empty] | No Data
57 | I | 334 | Bidyut Bikash Dinda | Unit-III | Coke Oven Mechanical | Reduce the average monthly general Maintenance Cost per ton of Coke Oven Plant from ₹28.6 to <₹25. | Decresing | ₹/Ton | Jul'25-Dec'25 | 28.6 | 25 | [8 empty] | No Data
58 | II | 7747 | Prasanta Basu | Unit-III | ISO | Reduction of Paper Consumption through Effective IMS Internal Audits & Competence-Based Training from 27620 to < 5524. | Decresing | Nos | Jan'23-Jan'25 | 27620 | 5524 | [8 empty] | No Data
59 | II | 2712 | Abdur Rowf | Unit-III | Store | Reducing Non moving items of Central store values from 6.3Cr. to <3.15Cr. INR | Decresing | Cr |  | 6.3 | 3.15 | [8 empty] | No Data
60 | I | 30103 | Suman Majumder | JSBIL | Operation (Chemist) | Reducing the cost of laboratory operation by optimizing chemical and machine uses . | Decresing | 0 | [11 empty] | No Data
61 | I | 47015 | Aniruddha Ray | Unit-IV | Accounts and Finance | Reduce the Invoice processing time of unit IV from --- to -----. | Decresing | 0 | [11 empty] | No Data
62 | I | 4924 | Ashok kumar Singh | Unit-III | Industrial Relationship | Increase the Contractual Manpower engagement of Unit-III from ---- per month to 100 % . | Increasing | % | [11 empty] | No Data
64 | II | 7780 | Hilary Joseph | Unit-III | Industrial Relationship | Reducing Manpower cost /MT 4.58 cr from 3.67 cost/MT | Decresing | Cost/MT | [11 empty] | No Data
65 | I | 16027 | Arijit Modi | JSBIL | Commercial | To Reducing the Despatch cycle time from --- hrs to ---- hrs of Jai salasar. | Decresing | [12 empty] | No Data
66 | II | 9517 | PK Swain | Unit-IV | Electrical | Improving power factor from ------- to -------- in Unit -IV. | Increasing | [12 empty] | No Data
68 | I | 6388 | Randhir Kumar | Unit-III | Business Excellence | [14 empty] | No Data
69 | I | 6389 | Avinash Kumar Mahato | Unit-III | Business Excellence | [14 empty] | No Data
70 | II | 48624 | Sidheswar Biswal | Unit-IV | Safety | Reducing unsafe condition per months from 406 to < 203. | Decresing | Nos | [11 empty] | No Data
71 | I | 7799 | Kamal kant | Mackeil | BE-Mackeil Opeeartion | [14 empty] | No Data
72 | I | 10223 | Amitava Dasgupta | HO | DIP Marketing | Re-establish the tender data base (tender missing) ------- reducing tender processing time from ----- to ----- without adverse implication. |  | Nos | [11 empty] | No Data
73 | II | 10860 | Souptik Mondal | HO | DIP Marketing | Reducing the freight cost per Km /MT from 580 to <----. |  | Per kM/MT | [11 empty] | No Data
74 | II | 11039 | Soumen Pal | HO | DIP Marketing | Re-establish the tendor data base (tendor missing) per month from -------to ----. | Increasing | Nos | [11 empty] | No Data
75 | I |  | Sanjib Pattnaik | UNIT-I | Human Resource |  | Decresing | [12 empty] | No Data
76 | I | 10642 | Amitava Mukherjee | HO | Human Resource | Improve the Manpower engagement of HO from -- % per month to --- % per month. | Increasing | 0 | [11 empty] | No Data
77 | I | 10811 | Roopam Rai | HO | Business Excellence | Development of New Products with High Demand for Open Die Forgings Plant". | Increasing | [12 empty] | No Data
78 | II | 3927 | Subhash Ghosh | Unit-III | Civil | Vendor cost optimization | Decresing | [12 empty] | No Data
79 | II | 3069 | Kamal Bandyopadhyay | Unit-III | Account | Reduce Avg Planned vs. Actual Cost Variation of the MBF Plantper month from 1449 to 1232. | Decresing | [12 empty] | No Data
80 | II |  | Prashnat Yadav | Mackeil | Estimation | To Increased PO Conversation Ratio | Increasing | [12 empty] | No Data
81 | II | 47561 | Mohammad Ahmad | Unit-IV | Human Resource | Optimize manpower cost of Unit -IV. | Decresing | [12 empty] | No Data